## Sheet1
Bug_ID | Module | Bug Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status
BUG_001 | Login | System allows login with invalid password | Enter valid username + wrong password → Click Login | Error message should display | User logged in successfully | High | High | Open
BUG_002 | Login | Login page crashes with invalid username | Enter wrong username → Click Login | Proper validation message should display | Application crashed | Critical | High | Open
BUG_003 | Login | Username validation missing | Leave username field empty → Click Login | Username required message should display | No validation shown | Medium | Medium | Open
BUG_004 | Login | SQL Injection vulnerability in login | Enter SQL injection input in username/password | Application should block invalid query | System allowed login | Critical | High | Open
BUG_005 | Cart | Duplicate products added incorrectly | Add same product multiple times | Product quantity should update correctly | Duplicate entries created | Medium | Medium | Open
BUG_006 | Cart | Removed product still visible in cart | Add product → Remove product | Product should disappear from cart | Product still displayed | High | High | Open
BUG_007 | Cart | Cart icon not opening cart page | Click cart icon | Cart page should open | Cart page not opening | Medium | High | Open
BUG_008 | Cart | Out-of-stock products can still be added | Add unavailable product to cart | Error message should display | Product added successfully | High | Medium | Open
BUG_009 | Cart | Cart data lost after page refresh | Add products → Refresh browser | Cart items should remain saved | Cart became empty | Medium | Medium | Open
BUG_010 | Checkout | Checkout proceeds without first name | Leave first name empty → Continue checkout | Validation should stop checkout | Checkout continued | High | High | Open
BUG_011 | Checkout | Checkout allows empty last name | Leave last name field empty | Validation message should display | Checkout completed | Medium | Medium | Open
BUG_012 | Checkout | Postal code validation missing | Leave postal code empty → Continue | Postal code required message | Order completed successfully | High | High | Open
BUG_013 | Checkout | Checkout possible with empty cart | Proceed to checkout without products | Checkout should be blocked | Order completed | Critical | High | Open
BUG_014 | Checkout | System crashes on invalid payment details | Enter invalid payment information | Payment failed message should display | Application crashed | Critical | High | Open
BUG_015 | Logout | Session remains active after logout | Logout → Click browser back button | User should redirect to login page | Dashboard reopened | High | High | Open
BUG_016 | Logout | Logout option not loading in menu | Open sidebar menu | Logout option should display | Menu failed to load | Medium | Medium | Open
BUG_017 | Logout | Multiple logout clicks crash application | Click logout button repeatedly | Application should handle safely | Application crashed | Medium | Medium | Open
BUG_018 | Logout | Session timeout not working | Keep application idle for long time | User should auto logout | Session still active | High | High | Open
BUG_019 | Logout | Logout during checkout freezes page | Start checkout → Logout | User should logout safely | Checkout page froze | Medium | Medium | Open
BUG_020 | Login | Password visible in plain text | Enter password in password field | Password should be masked | Password visible on screen | High | Medium | Open